## Guide
IAC INTERNSHIP PROGRAM 2023
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
|  | PROJECT NAME | Career Path Prediction and Guidance System Student Placement Prediction
|  | PROJECT MANAGER | Harshada Topale
|  | PROJECT DELIVERABLE | Job Cloud Job Portal
|  | PROJECT SCOPE | Predictive Modeling
|  | PROJECT START DATE | 2024-06-05
|  | PROJECT END DATE | 2024-08-23
|  | OVERALL PROGRESS | Completed
IAC Internship Progra 2023 - Machine Learning
|  | PROJECT START DATE | 2024-06-05
|  | DOCUMENT TITLE: | PROJECT SCHEDULE
|  | Document created By: | Prathamesh Bawane
[14 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08 | [6 empty] | 2024-07-15 | [6 empty] | 2024-07-22
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | time axis 2024-05-27 to 2024-07-28
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2024-05-27 to 2024-07-28
1 | Week 1 [Orientation & Project Planning]
1.1 | 1 | Internship Kickoff | Orientation Session |  |  | Prathamesh Bawane | 2024-06-05 | 2024-06-06 |  |  | Completed | 100 Percent
1.1.1 |  | [Activity 1.1]
1.1.2 |  | [Activity 1.1]
1.1.3 |  | [Activity 1.1]
1.1.4 |  | [Activity 1.1]
1.2 |  | Project Planning | Understanding Requirements |  |  | Prathamesh Bawane | 2024-06-06 | 2024-06-09 |  |  | Completed | 100 Percent
1.2.1 |  | [Activity 1.2]
1.2.1.1
1.2.3 |  | [Activity 1.2]
2 | Week 2 [Dataset Acquisition & Setup]
2.1 | 2 | Data Collection | Download PS2 Dataset & Placement Dataset |  |  | Prathamesh Bawane | 2024-06-10 | 2024-06-14 |  |  | Completed | 100 Percent
Week 3 [Data Exploration & Cleaning]
3.1 | 3 | Exploratory Data Analysis | Understand attributes |  |  |  | 2024-06-17 | 2024-06-21 |  |  | Completed | 100 Percent
3.2 | 3 | Data Cleaning | Handle nulls/outliers |  |  |  | 2024-06-19 | 2024-06-22 |  |  | Completed | 100 Percent
Week 4 [Feature Engineering]
4.1 | 4 | Feature Selection | Feature Selection |  |  |  | 2024-06-24 | 2024-06-28 |  |  | Completed | 100 Percent
4.2 | 4 | Graduation Year Logic | Derive expected year |  |  |  | 2024-06-26 | 2024-06-28 |  |  | Completed | 100 Percent
5 | Week 5 [Model Development: Career Path]
5.1 | 5 | Model Selection | Train ML Models for Career Guidance |  |  |  | 2024-07-01 | 2024-07-05 |  |  | Completed | 100 Percent
6 | Week 6 [Model Development: Placement Prediction]
6.1 | 6 | Classification Algorithms | Train ML Models on Placement Status |  |  |  | 2024-07-08 | 2025-07-12 |  |  | Completed | 100 Percent
7 | Week 7 [Model Evaluation & Tuning]
7.1 | 7 | Evaluate Results | Accuracy, Precision, Recall |  |  |  | 2024-07-15 | 2024-07-19 |  |  | Completed | 100 Percent
8 | Week 8 [Insight Generation]
8.1 | 8 | Analyze Career Suggestions | Generate Recommendations |  |  |  | 2024-07-22 | 2024-07-26 |  |  | Completed | 100 Percent
8.2 | 8 | Analyze Placement Patterns | Feature Importance |  |  |  | 2024-07-24 | 2024-07-26 |  |  | Completed | 100 Percent
9 | Week 9 [Presentation & Documentation]
9.1 | 9 | Create Final Notebooks | Clean code & comment |  |  |  | 2024-07-29 | 2024-08-02 |  |  | Completed | 100 Percent
10 | Week 10 [Presentation & Documentation]
10.1 | 10 | Report Writing | Draft project reports |  |  |  | 2024-08-05 | 2024-08-09 |  |  | Completed | 100 Percent
11 | Week 11 [Finalization & Submission]
11.1 | 11 | Prepare Presentation Slides | WBS, Schedule, Logs |  |  |  | 2024-08-12 | 2024-08-16 |  |  | Completed | 100 Percent
12 | Week 11–12 [Finalization & Submission]
12.1 | 12 | Submit Final Deliverables | Upload and Submit |  |  |  | 2024-08-19 | 2024-08-23 |  |  | Completed | 100 Percent
Note on H17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you