## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
DOMAIN NAME: | Machine Learning
INTERN NAME: | Prathamesh Bawane
PROJECT NAME: | Career Path Prediction and Guidance System, Student Placement Prediction
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2024-05-06
PROJECT NAME | Career Path Prediction and Guidance System, Student Placement Prediction
PROJECT ID | N/A
PROJECT MANAGER | Prathamesh Bawane
PROJECT SPONSOR | Cloud Counselage Pvt. Ltd.
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2024-10-07 | Delay in cleaning and preprocessing large dataset | Data Handling | Yes | Allocate more time for data cleaning phase | Adjusted project timeline | Project Developer | Solved | Took 2 extra days
2 | 20/07/2024 | Model accuracy lower than expected during testing | Machine Learning | Yes | Try different ML models and hyperparameter tuning | Performed model tuning | Project Developer | Solved | Achieved better results with Random Forest
3 | 2024-01-08 | Difficulty in mapping career guidance output to student skill data | Logic/Design | No | Improve rule-based mapping logic | Updated algorithm | Project Developer | Solved | Improved guidance accuracy
4 | 15/08/2024 | Misalignment between UI and backend prediction output display | Integration | Yes | Regular integration testing | Fixed via UI-backend sync | Project Developer | Solved | Conducted weekly testing
5 | 2024-05-09 | Limited time for documentation due to last-minute changes | Project Management | No | Plan buffer time for documentation | Added documentation buffer | Project Developer | Solved | Delivered on time