## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 3 | 0 | 1 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Career Path Prediction and Guidance System, Student Placement Prediction |  | Project Id: |  | Project Manager: | Prathamesh Bawane |  |  | Assumption | 2 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 2 | 1 | 1 | 0 | 0 | 0
| DOCUMENT VERSION: |  |  | Last Updated date: | 2024-08-12 | Project Team Lead: |  |  |  | Dependency | 1 | 0 | 1 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 8 |  |  |  |  | 4
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Lack of access to high-quality datasets | Delayed model training and inaccurate predictions | Use publicly available datasets; request support from the internship team | Project Manager | High |  | Open | Risk
2 | Risk | Inadequate system performance due to limited computing power | Slow development/testing cycle | Use cloud-based environments like Google Colab | Project Manager | Medium |  | Closed | Assumption
3 | Assumption | Datasets provided are clean and relevant | May lead to faster development | Have data cleaning and validation steps early | Team Lead | Low |  | Closed | Issue
4 | Issue | Model accuracy below expected threshold | May fail to meet guidance/prediction requirements | Try different ML algorithms and hyperparameter tuning | Project Manager | Critical |  | Open | Dependency
5 | Dependency | Availability of guidance from mentors/supervisors | Delay in task clarity and approvals | Schedule weekly sync-up calls or use forums for support | Project Manager | High |  | Open
6 | Risk | Team member unavailability during critical phases | Missed milestones and task delays | Set backup ownership for key deliverables | Team Lead | Medium |  | Closed | Open
7 | Assumption | Interns will have basic Python/ML knowledge | Assumed less time on training | Provide initial onboarding resources | Project Manager | Low |  | Closed | Closed
8 | Issue | Conflicting task deadlines across both projects | Affects quality and timely submission | Prioritize tasks; use project schedule efficiently | Project Manager | High |  | Open
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24